## Sheet1
SrNo | Epic Story - Api Docs Work | Story Points | Comments
1 | Story : Spike : Api Documentation Analysis/Functional requiremnt gathering | 13
A. Analysis of stripe api documentation and concur developer page.
B. Overview of swagger apis and custmization
C. Proposed technolgoies on work - Angular, NodeJS, Bootstrap, Database
D. Define Api docs basic layout and strctures.
2 | Story : Spike : Swagger Capability Analysis | 8
A. Integrate sample swagger endpoints in to test user interface.
B. Explore on Swagger UI custom plugins apis
C. Explore on Swagger custom layouts
D. Explore on Swagger Custom presets
E. Integrate BAQS QA endpoints on custom user interface
3 | Story : Code setup abd Define Code strcutre for Api docs work | 5
A. Machine setup for Angular and Nodejs work
B. Prepare angular and nodejs coding standards.
C. Create generic code structure so new code will easily intergrated
4 | Story : Design : Creation of user iinterface for Api docs pages - Wireframe/Layouts | 13
A. Prepare a logo and name for this project - Eg. Bank Unify
B. Design Homepage user interface
C. Design : Api Inventory user interface
D. Design : Service level description user interface
E. Design : Swagger endpoints display user interface
F : Testing : Device compability and Various sceen resolution check
5 | Story : Spike : List down all services will consume/include in api docs work | 5
A. Analysis and get all Swagger services and endpoints.
B. Analysis and get all non-swagger services.
6 | Story : Service integration with api documentation dashboard (BankUnify) | 8
A. Design data template for service level information
B. Collect and intergrate service level info into the defined template
7 | Story : Spike : Get service specific data dynamically | 8
A. Approach I: Get data from database eg. MongoDB/Sql Server
B. Approach II : Get data from .json files hosted on service repo server
C. Propose solution based on approach selected.
8 | Story : Develop a solution to get BAQS service data dynamically | 13
A. Develop a solution based on selected approach.
B. Creation of database schema (DB/.json files)
C. Integrate dynamic data solution to api docs work
9 | Story : Spike : Publish Api Portal | 5
A. Analysis on how to add/update/delete existing and new service
Configurationa required for creating new api publisher portal
C. Chages required to be done on Api documentation portal
10 | Story : Design & Develop api publisher portal | 13
A. Design api publisher portal - Create wireframes/layouts
B. Code for integration of api publisher and database approach
C : Testing : Device compability and Various sceen resolution check
11 | Story : Swagger Configuration changes - Service lelvel changes by Service owner | 5
A. List down all configurations parameters needed for swagger service
B. Integration of new changes into api documentation work
Total Story Points = 96